## PerformanceinInitiating
Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed / denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for Delay | Comments | Reasons for delay correspond to:
17/EE/0508 | 233813 | HRA Approval | FAB in DED Trial | Yes | 2018-04-18 | 39 | 9 | 48 |  | 2016-10-10 | 2018-03-01 | 2018-02-28 | 2018-03-01 | 2018-04-09 | 2018-04-13 | [10 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | Delays between DSI and DSS due to being Sponsor and awaiting grant application process | Please Select...
17/EE/0382 | 220851 | HRA Approval | PROFILE | No |  | 2 |  |  |  | 2017-02-03 | 2018-02-19 | 2017-11-02 | 2018-01-26 | 2018-02-21 | 2018-05-03 | [5 empty] | Y |  |  |  |  | SpreadsheetTwoConstants.DATA_STRING_SELECT |  | NHS Provider
17/WM/0239 | 223251 | HRA Approval | AIR Ankle Injury Rehab | No |  | 1 |  |  |  | 2017-09-15 | 2018-06-05 | 2018-07-04 | 2017-11-15 | 2018-06-06 | 2018-06-06 | [10 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT |  | Please Select...
16/NS/0053 | 201313 | HRA Approval | C-GALL | No |  | 95 |  |  |  | 2018-02-20 | 2018-03-12 | 2016-09-01 | 2018-03-12 | 2018-06-15 | 2018-06-14 |  |  |  | Y | Y | [5 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | Delay in organising SIV then further delay following SIV on 14/06/2018 awaiting Site File and resources from Sponsor | Both
17/YH/0120 | 208838 | HRA Approval | DISC | No |  | 8 |  |  |  | 2018-02-13 | 2018-07-16 | 2017-05-25 | 2018-07-16 | 2018-07-24 | 2018-09-07 | [10 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT |  | Please Select...
18/SW/0130 | 246372 | HRA Approval | S-FLEX UK-II | No |  | 27 |  |  |  | 2018-05-24 | 2018-07-05 | 2018-06-24 | 2018-07-10 | 2018-08-01 | 2018-08-01 |  |  |  | Y | [6 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | Sponsor updated device just after SIV so cannot start until new CE marking - due February 2019 | Sponsor
18/LO/1011 | 245031 | HRA Approval | Show RESPECT | No |  | 73 |  |  |  | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2018-08-24 | 2018-08-24 | 2018-11-08 |  |  |  | Y | [6 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | Sponsor opening sites in 'waves' | Sponsor

## PerformanceinDelivering
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
ST1314/16 | 317544 | MILES-UK | Number Agreed | 100 | 100 | Date Agreed | 2018-07-31 | 114 | 2018-07-31 | 114 | Recruitment Finished | Once site reached target, sponsor requested we continue to recruit to boost numbers
15/WS/0170 | 184797 | ETNA-VTE | Number Agreed | 5 | 5 | Date Agreed | 2018-08-31 | 7 | 2018-08-31 | 7 | Recruitment Finished | Asked by sponsor to continue recruitment once target reached
Note on D1: Drop down options. Please indicate whether the trial has a fixed target (Number Agreed), range target (Range Agreed) or no target agreed or available (Not Available /Not Agreed)
Note on G1: Drop down options. Indicate if a target date has been agreed.
Note on H1: Format dd/mm/yyyy. Please show the date agreed to recruit patients. Leave blank if unavailable.
Note on I1: Please report the total number of patients recruited at the agreed target date.
Note on J1: Please only include records for commercial trials which have closed to recruitment within the reporting window. Format dd/mm/yyyy.
Note on K1: Please report the total number of patients recruited.
Note on M1: Please use the free text comment box for more information about the trial. Character limit: 500