## PiI
Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
18/LO/1674 | 244500 | HRA Approval | e-path Study | Yes | 2019-07-11 | 73 | 17 | 90 | 2019-06-24 | 2019-03-26 | 2019-04-12 | 2018-11-16 | 2019-04-12 | 2019-06-24 | Please Select... | 2019-06-24 | Y | [9 empty] | Delay in HRA approval adding site via amendment | Neither
N/A | 251770 | HRA Approval | NED-APRIQOT | Yes | 2019-12-27 | 43 | 16 | 59 |  | 2019-07-26 | 2019-10-29 | 2019-02-05 | 2019-11-29 | 2019-12-11 | Please Select... | 2019-12-18
18/ES/0119 | 245233 | HRA Approval | STATIC | No |  | 4 |  |  |  | 2019-06-13 | 2019-09-12 | 2018-11-09 | 2019-09-13 | 2019-09-16 | Please Select... | 2019-10-30
15/NS/0070 | 183761 | HRA Approval | BASIL-3 | No |  | -402 |  |  |  | 2017-11-13 | 2019-10-10 | 2016-04-27 | 2018-07-24 | 2018-09-03 | Please Select... | 2019-10-29 |  | Y | [8 empty] | Halted nationally Dec 2018. Re-invited 15/05/2019 | Sponsor
19/NW/0158 | 259931 | HRA Approval | SCIENCE | No |  | 35 |  |  |  | 2019-06-07 | 2019-11-04 | 2019-03-25 | 2019-12-03 | 2019-12-09 | Please Select... | 2019-12-10
17/EE/0250 | 219937 | HRA Approval | ContactMe-IBS | Yes | 2019-11-05 | 0 | 7 | 7 |  | 2019-10-18 | 2019-10-29 | 2017-07-17 | 2019-10-29 | 2019-10-29 | Please Select... | 2019-10-29

## PiD
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
Nil to report