## PerformanceInInitiating
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected & Date Site Confirmed | Duration between Date Site Confirmed & First Participant Recruited | Duration between Date Site Selected & First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed/ denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for Delay | Comments | Reasons for delay correspond to:
17/YH/0120 | 208838 | DISC | Yes | 2019-03-13 | 8 | 232 | 240 | 2018-02-13 | 2018-07-16 | 2017-05-25 | 2018-07-16 | 2018-07-24 | 2018-09-07 | [6 empty] | Y |  |  |  | SpreadsheetTwoConstants.DATA_STRING_SELECT |  | NHS Provider
18/SC/0243 | 240684 | ORION-4 | Yes | 2019-04-24 | 43 | 190 | 233 | 2018-03-05 | 2018-09-03 | 2018-10-10 | 2018-10-10 | 2018-10-16 | 2018-10-16 |  |  |  | Y | [6 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | Sponsor requested site to be ready but phased roll out of sites opening | Sponsor
18/SS/0033 | 242190 | BICS | Yes | 2019-05-16 | 63 | 195 | 258 | 2018-06-18 | 2018-08-31 | 2018-08-09 | 2018-08-31 | 2018-11-02 | 2019-01-09 | [6 empty] | Y |  |  |  | SpreadsheetTwoConstants.DATA_STRING_SELECT |  | NHS Provider
18/LO/1674 | 244500 | e-path Study | No |  | 73 |  |  | 2019-03-26 | 2019-04-12 | 2018-11-16 | 2019-04-12 | 2019-06-24 | 2019-06-24 | Y | [9 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | Delay in HRA approval adding site via amendment | Neither
16/LO/1750 | 210497 | INNODIA | No |  |  |  |  | 2019-04-11 | 2019-05-30 | 2019-11-09 | 2019-05-30 | [12 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT |  | Please Select...
18/SW/0130 | 246372 | S-FLEX-UK II | No |  | 27 |  |  | 2018-05-24 | 2018-07-05 | 2018-06-24 | 2018-07-10 | 2018-08-01 | 2019-08-01 |  |  |  | Y | [6 empty] | SpreadsheetTwoConstants.DATA_STRING_SELECT | SIV 17/08/2018 however Sponsor awaiting CE marking for new stent. Continued chasing sponsor until April 2019 but no reply. Presumed study no longer going ahead. | Sponsor

## PerformanceInDelivering
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
13/NI/0123 | 317544 | MILES-UK | Number Agreed | 100 | 100 | Date Agreed | 2018-07-31 | 114 | 2018-07-31 | 114 | Recruitment Finished | Once site reached target, sponsor requested we continue to recruit to boost numbers
15/WS/0170 | 184797 | ETNA-VTE | Number Agreed | 5 | 5 | Date Agreed | 2018-08-31 | 7 | 2018-08-31 | 7 | Recruitment Finished | Asked by sponsor to continue recruitment once target reached
16/NW/0305 | 201856 | Ipsen223 (Content-2) | Number Agreed | 4 | 4 | Date Agreed | 2019-06-30 | 0 | 2018-10-01 | 0 | Withdrawn By Sponsor | Poor recruitment nationally so study closed by Sponsor
Note on D1: Drop down options. Please indicate whether the trial has a fixed target (Number Agreed), range target (Range Agreed) or no target agreed or available (Not Available /Not Agreed)
Note on G1: Drop down options. Indicate if a target date has been agreed.
Note on H1: Format dd/mm/yyyy. Please show the date agreed to recruit patients. Leave blank if unavailable.
Note on I1: Please report the total number of patients recruited at the agreed target date.
Note on J1: Please only include records for commercial trials which have closed to recruitment within the reporting window. Format dd/mm/yyyy.
Note on K1: Please report the total number of patients recruited.
Note on M1: Please use the free text comment box for more information about the trial. Character limit: 500