| Ref | Task/Actions | Related Report(s) | Protected characteristics | Action Owner | Named EDI Lead | Start | Due Date | Status | Quarter 4 - 1 October - 31Dec 2024 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Develop an inclusive recruitment, promotion & appointment process |  |  |  |  | Apr-23 | Mar-25 | In progress |  |
| 1.4 | Complete a review to work towards more diverse recruitment panels. This will focus on developing a work plan to develop appropriately trained staff and develop a Trust approach and policy. | WDES 1 WRES 1 Gender Pay Gap | Disability Race | Jim Machon Associate Director of HR | Angie Heilmann | 01/11/2024 | 28/02/2025 | In progress | A monthly EDI/HR/Occie Health meeting is now scheduled providing opportunity to work collaboratively on actions such as this. Next meeting 6.11.24 |
| 1.6 | Recruitment team to review the recruitment process including wording and literature used in advertising (stated commitments, reasonable adjustments, access and inclusion) to increase the number of applicants with a disability. | WRES 1 Rainbow Badge Accreditation | Disability LGBT+ Race | Jim Machon Associate Director of HR | Angie Heilmann | 01/01/2024 | 31/03/2025 | In progress | A monthly EDI/HR/Occie Health meeting is now scheduled providing opportunity to work collaboratively on actions such as this. Next meeting 6.11.24 |
| 1.8 | Develop a process to understand the reasons for the low transfer of uptake to interview from BAME candidates and those with a disability. Audit to be undertaken. | WDES 1 WRES 1 | Disability Race | Jim Machon Associate Director of HR | Angie Heilmann | 01/10/2023 | 30/12/2024 | In progress | A monthly EDI/HR/Occie Health meeting is now scheduled providing opportunity to work collaboratively on actions such as this. Next meeting 6.11.24 |
| 1.11 | Undertake an initiative for "What's itt got to do with you?" for the importance of declaration/data capture plus how the data is generic, anonymised and confidential - this is extended to the areas of Sexual Orientation and Religion ad Belief which also have data validity issues due to non or low declaration. Aim to improve declaration by 1% for Race and 5% for disability | WRES1 WDES3 WRES3 | All Disability Race | Head of Health Inequalities & Inclusion | AH & MD | 30/10/2023 | 31/03/2025 | In progress | Promote the importance of self-declaration at the winter staff engagement event |
| 1.12 | Continue work on the flexible working policy in line with the feedback from our staff survey. Embed the process and review through future staff survey results | Gender Pay Gap WRES WDES Dignity at Work | All | Fiona MacDonald, Director of Culture & OD | Maureen Drummond | 01/04/2023 | 30/04/2025 | In progress | SDN took part in Compassionate & Inclusive week |
| 2 | Build zero tolerance to bullying, harassment & discrimination |  |  |  |  |  |  | In progress |  |
| 2.1 | Continue with the campaign ‘no excuse for abuse’ - Promotional plan through Comms team and local partners within BLMK. E&D Communication Plan to be put in place. | WDES 5 WRES 5 BAPIO Dignity at work report Sexual safety Charter 2023 Too Hot to Handle Brp | Disability Race Gender /sex Gender reassignment | Head of Health Inequalities & Inclusion | Maureen Drummond | 31/07/2024 | 31/12/2024 | In progress | 6.11.24 meeting with Comms Team to discuss |
| 2.2 | Using the respectful resolution approach as part of the embedding values and a Kind Life project. | WDES 6 WRES 6 WDES 8 WRES 8 BAPIO Dignity at work report Sexual safety Charter 2023 Too Hot to Handle Brp | Disability Race Gender/sex Gender reassignment | Hazel Rawdon Smith, Associate Director of OD | Angie Heilmann | 01/04/2023 | 31/10/2024 | In progress | Respectful Resolution a available to all Trust staff EDU Leads attending training. Nov & Dec |
| 2.3 | Increasing diverse speak up champions within the Trust and maintain communication about their role and access. | WDES 4 WRES 8 BAPIO Dignity at work report Sexual safety Charter 2023 | Disability Race Gender/sex Gender reassignment | Fiona MacDonald, Director of Culture & OD | Maureen Drummond | 31/07/2023 | 31/10/2024 | In progress | FTSU Guardian routinely attend monthly SDN meetings to promote their work. |
| 3.1 | Review the data for the disciplinary information across the Trust to determine trends relating to protected characteristics. (action re-worded 30.10.24) | WRES 3 | Race | Jason Rosenblatt, Deputy Director of HR | Angie Heilmann | 31/03/2023 | 31/01/2025 | In progress | Due date extended 31.1.25 Action will be discussed at next meeting EDI/HR/Occie health 6.11.24 |
| 3.2 | Use "a Kind Life" respectful resolution approach to proactively deal with issues at an early stage before formal processes commence in a manner that is supportive to staff. Promote cultural awareness skills boosters for line managers and network members along with FTSU and Peer listeners. Implement training. | WRES 3 BAPIO Dignity at work report. Sexual safety Charter 2023 | Race | Fiona MacDonald, Director of Culture & OD | Maureen Drummond | 30/06/2023 | 31/07/2024 | In progress | Respectful Resolution training available to all Trust staff EDU Leads attending training – Nov & Dec |
| 3.3 | Engage with disabled staff through the Staff Diversity Network to identify feedback on what it is like to work for the Trust and improvements that could be made. | WDES 4 | Disability | Head of Health Inequalities & Inclusion | Angie Heilmann | 01/04/2024 | 31/12/2024 | In progress | Recently appointed a further Disability & LTC -Single Point of Contact (SPOC) to work in partnership with current SPOC |
| 3.4 | Improve Trust wide communications and in particular highlight areas where BHFT are making good progress and areas where more work is required. E&D Communication Plan to be in place | WDES 4 BAPIO Dignity at work report. | Disability | Head of Health Inequalities & Inclusion | AH & MA | 01/04/2024 | 31/12/2024 | In progress | SDN Newsletter 1st Edition available - 2nd Edition Dec |
|  | WORKSTREAM 5: [Equal Opportunities] |  |  |  |  | 31/03/2023 | 31/03/2025 | In progress |  |
| 5 | Advance equality of opportunity between person who share a protected characteristic and person who do not. |  |  |  |  |  |  |  |  |
| 5.1 | E&D Communication Plan. Better Trust wide communications highlighting areas where BHFT are progressing and doing well, plus areas being worked on are needed. With out these perceptions and narrative will remain the same and the bigger picture will be missed. | WDES 7 WRES 7 | Disability Race | Head of Health Inequalities & Inclusion | AH & MD | 31/07/2023 | 31/12/2024 | In progress | 6.11.24 Meeting to discuss EDI Framework comms plan |
| 5.6 | To further implement the talent management strategy within the organisation including career conversations. Quarterly review through the Workforce Committee | WDES 7 WRES 7 | Disability Race | Fiona MacDonald, Director of Culture & OD | Maureen Drummond | 01/04/2023 | 31/07/2024 | In progress |  |
| 5.7 | Develop a Trust Disability Policy that includes a 'Reasonable Workplace Adjustment Protocol' seeking the support of key stakeholders including the Staff Diversity Network | WDES 3 BAPIO Dignity at Work Report National EDI Plan 2023 | Disability | Head of Health Inequalities & Inclusion | Angie Heilmann | 04/07/2024 | 31/03/2025 | In progress | EDI & HR agreed a phased approach - First Phase - Inclusion Passport - Action 5.7 & 5.8 will be discussed at next meeting EDI/HR/Occie health 6.11.24 |
| 5.8 | Develop a Trust Inclusion Passport to support staff communication with line managers and supervisors regarding protected characteristics. | WDES 3 BAPIO Dignity at Work Report National EDI Plan 2023 | All | Head of Health Inequalities & Inclusion | Angie Heilmann | 04/07/2024 | 31/12/2024 | In progress |  |
|  | WORKSTREAM 6: [Board Representation] |  |  |  |  | 01/06/2024 | 31/03/2025 | In progress |  |
| 6 | Engaging everyone in Inclusive By Instinct |  |  |  |  |  |  |  |  |
| 6.4 | Create a standard monthly report to Board of status of EDI programme | WDES 9 WRES 9 | All | Victoria Parsons, Associate Director of Corporate Governance | AH & MD | 30/10/2023 | 31/08/2024 | On going |  |
| 6.6 | Develop an EDI Framework 'Inclusive by Instinct' as the platform to build the EDI Strategy | WRES WDES NHS ED Improvement Plan | All | Head of Health Inequalities & Inclusion | AH & MD | 26/09/2024 | 31/12/2024 | In progress | EDI Framework - presented to Workforce Committee 9.11.24 - Next step Presentation to the Board |
| 6.7 | Create a new Trust EDI Strategy 'Inclusive by Instinct' building on the EDI Framework | WRES WDES NHS ED Improvement Plan | All | Head of Health Inequalities & Inclusion | AH & MD | 31/12/2024 | 31/03/2025 | In progress | Awaiting sign off E by the Board - EDI Framework |
|  | WORKSTREAM 7: [Health Inequalities] |  |  |  |  | 30/09/2023 | 31/03/2025 |  |  |
| 7 |  |  |  |  |  |  |  |  |  |
| 7.4 | Develop a response to the Denny review when it is finalised. Denny focusses on Local Inequalities and access to Trust Services | WRES National EDI Plan 2023 Denny Report | All | Head of Health Inequalities & Inclusion | Maureen Drummond | 05/09/2023 | 31/03/2025 | In progress | 7.11.24 Attending BLMK event -Spotlight on the Denny Review |
| 7.6 | Develop a plan for patient information review to target priority health inequality areas. | WDES WRES NHS ED Improvement Plan | All | Head of Health Inequalities & Inclusion | AH & MD | 26/09/2024 | 31/03/2025 | In progress |  |